## Project planner
Project planner
[5 empty] | Marking of period: | 1 |  |  | Schedule duration | [5 empty] | Actual start date |  |  |  |  | % Complete |  |  |  |  | Actual (out of schedule) | [7 empty] | % Complete (out of schedule)
ACTIVITY | START OF PLANNING | DURATION OF PLANNING | ACTUAL START DATE | ACTUAL DURATION | PERCENTAGE COMPLETE | PERIODS
[6 empty] | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61
Research | 35 | 3 | 35 | 3 | 80%
Jogging system | 37 | 3 | 37 | 3 | 100%
Coordinate system | 40 | 4 | 38 | 0 | 25%
GUI (Graphical User Interface) | 44 | 4 | 0 | 0 | 0%
Porgrams | 48 | 4 | 0 | 0 | 0%
Tool integration | 52 | 4 | 0 | 0 | 0%
Pendant | 0 | 0 | 0 | 0 | 0%